DEPI – Digital Egypt Pioneers Initiative  |  Track: Junior Data Analysis

Data Lens

1. Project Planning & Management

DEPI submission item: Project Planning & Management (Project Proposal, Project Plan, Task Assignment & Roles, Risk Assessment & Mitigation Plan, KPIs)

| Team member | Role |
| --- | --- |
| Shahd Mahmoud Abdelmagid | Team Leader |
| Eman Ali Mostafa | Member |
| Malak Hassan Mahmoud | Member |
| Farah Khaled Fathy | Member |
| Menna Abdelnasser Ramadan | Member |
| Mariam Baher Mohsen | Member |
| Instructor: Noran El Zeky | Lecturer / evaluator |

Version 1.0 (draft)  |  October 2026

# 1. Project Proposal Summary

Project name: Data Lens – Country Data Comparison Dashboard (World Development Indicators).

Objective: turn the raw, inconsistent World Bank WDI extract (22 countries, 74 indicators, 2000–2025) into a clean, validated data model and an interactive multi-page dashboard that lets users compare countries, including Egypt, across economy, health, education, labor, and infrastructure.

## Scope

In scope: cleaning and standardizing WDI_Data.xlsx; star-schema data model; DAX measures; a dashboard with at least three pages (country overview, country comparison, trends), map, and drill-through; testing; documentation; final presentation; infographic.

Out of scope: collecting data from sources other than the provided WDI workbook; forecasting or machine-learning models; real-time data refresh; mobile app.

The full proposal (weekly tasks per team member) is in the file Data_Lens_Project_Proposal.docx.

# 2. Project Plan

## Timeline and milestones

| Phase | Planned start | Planned end | DEPI deadline | Lead |
| --- | --- | --- | --- | --- |
| Project Planning & Management | 01 Oct 2026 | 16 Oct 2026 | 16 Oct 2026 | Shahd |
| Requirements Gathering | 05 Oct 2026 | 16 Oct 2026 | 16 Oct 2026 | Mariam, Farah |
| System Analysis & Design | 19 Oct 2026 | 06 Nov 2026 | 06 Nov 2026 | Malak, Menna |
| Week 1 – Data Understanding & Cleaning | 01 Nov 2026 | 07 Nov 2026 | – | Eman |
| Week 2 – Data Modeling & DAX | 08 Nov 2026 | 14 Nov 2026 | – | Malak |
| Week 3 – Dashboard Development | 15 Nov 2026 | 21 Nov 2026 | – | Farah, Menna |
| Week 4 – Testing & Documentation | 22 Nov 2026 | 28 Nov 2026 | – | Mariam |
| Implementation complete (source code & execution) | – | 28 Nov 2026 | 30 Nov 2026 | Shahd |
| Final presentation prep & buffer | 29 Nov 2026 | 04 Dec 2026 | 04 Dec 2026 | Shahd |

Note: Dates in the DEPI deadline column come from the Project Documentation Guidelines. The planned start/end dates are the team’s proposed schedule and should be confirmed with the instructor. The final project discussion takes place in Week 21 of the program.

Figure 1 – Gantt chart

## Deliverables

| # | Deliverable | Owner |
| --- | --- | --- |
| 1 | Project Proposal, Project Plan, Roles, Risks, KPIs | Shahd |
| 2 | Requirements document (stakeholders, user stories, use cases, FR/NFR) | Mariam, Farah |
| 3 | System Analysis & Design document (diagrams, schema, wireframes) | Malak, Menna |
| 4 | Cleaned dataset + data quality log + list of countries/indicators lacking data | Eman |
| 5 | Power BI data model and DAX measures | Malak |
| 6 | Power BI dashboard (.pbix, 3+ pages, map, drill-through) | Farah, Menna |
| 7 | Test plan, test cases, bug reports | Mariam |
| 8 | User manual and technical documentation | Mariam, Malak |
| 9 | Project infographic and final presentation (PPT/PDF) | Shahd, Mariam |
| 10 | GitHub repository with all files and README | Shahd |

## Resource allocation

| Resource | Type | Use |
| --- | --- | --- |
| Team of 6 members | Human | Roles in section 3 |
| Power BI Desktop | Software | Cleaning (Power Query), modeling, DAX, dashboard |
| Microsoft Excel | Software | Inspecting the source workbook and validating values |
| GitHub (organization repository) | Platform | Version control and delivery of all project files |
| WDI_Data.xlsx | Data | Source data: Data sheet and Series - Metadata sheet |

# 3. Task Assignment & Roles

| Member | Role | Responsibilities |
| --- | --- | --- |
| Shahd Mahmoud Abdelmagid | Team Leader | Coordination, communication with the instructor, task tracking, GitHub uploads, final presentation |
| Eman Ali Mostafa | Data Cleaning Lead | Power Query cleaning: country names, missing values, duplicates, data quality log |
| Malak Hassan Mahmoud | Data Modeling & DAX Lead | Star-schema model, relationships, DAX measures |
| Farah Khaled Fathy | Dashboard Developer | Pages 1–2 (overview and comparison), KPI cards, slicers |
| Menna Abdelnasser Ramadan | Dashboard Developer / UI-UX | Page 3 (trends), map, drill-through, theme and UI/UX |
| Mariam Baher Mohsen | QA & Documentation | Test cases and bug reports, user manual, technical documentation, infographic |

Note: This split is the team’s working draft and can be adjusted. At the final discussion each member must explain the work they delivered.

# 4. Risk Assessment & Mitigation Plan

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Inconsistent country names (e.g. USA, United States of America, united states) break relationships and totals | High | High | Mapping table in Power Query; test that exactly 22 countries remain |
| R2 | About 20% of year cells hold ".." (7,521 of 37,675) and a few hold text such as "-" or "295,282.00" | High | Medium | Convert ".." and "-" to null; convert text numbers; show "no data" instead of zero |
| R3 | Year 2009 is missing from the source columns | Certain | Low | Document it; trends show a gap; YoY measure handles blanks |
| R4 | Duplicate and empty rows (6 duplicate country–indicator rows, 100 empty rows) | Certain | Medium | Remove duplicates by key; list empty rows in the data quality log |
| R5 | 6 indicators have no entry in the metadata sheet; 1 indicator has no values at all | Medium | Low | List them as lacking data; exclude from comparison visuals |
| R6 | The design deadline (6 Nov) overlaps with the start of implementation | Medium | Medium | Start cleaning in parallel; freeze the data model design early |
| R7 | .pbix is a binary file; two members editing it causes lost work on GitHub | Medium | High | One editor per .pbix at a time; short-lived feature branches; leader merges |
| R8 | Team member unavailable or unequal workload | Medium | Medium | Weekly check-in; each task has a backup owner |
| R9 | Power BI Service publishing may need a license | Medium | Low | Deliver the .pbix on GitHub as the primary deliverable; web publishing is optional |
| R10 | Scope creep (extra pages/indicators) | Medium | Medium | Keep to the agreed 3+ pages; extras only after testing is complete |

# 5. Key Performance Indicators (KPIs)

| KPI | Metric | Target | How measured |
| --- | --- | --- | --- |
| Data accuracy | Sampled dashboard values equal to source values | 100% of 30 sampled values | Test case TC-D06 |
| Standardization | Distinct country names in the model | 22 | Test case TC-D01 |
| Data completeness handling | ".." or text values left in the Value column | 0 | Test cases TC-D02, TC-D03 |
| Responsiveness | Time for a visual to refresh after a slicer change | ≤ 5 seconds | Test case TC-N01 |
| Quality | Test cases passed | ≥ 95% | Test report |
| Coverage | Dashboard pages delivered | ≥ 3 | Dashboard review |
| Schedule | DEPI deadlines met | 4 of 4 | Plan vs. actual dates |
| Documentation | Required documents uploaded to GitHub | 100% | Checklist in README |
| Team contribution | Members with a documented deliverable | 6 of 6 | Task board / commit history |

Note: KPI targets are proposed by the team and should be confirmed with the instructor.