DEPI · Digital Egypt Pioneers Initiative

Track: Data Analysis

Project Proposal

DevCompare – Development Indicators Comparison

Project: DevCompare – Development Indicators Comparison (Egypt, Nigeria, India, Brazil, Türkiye)

| Team Leader | Shahd Mahmoud Abdelmagid |
| --- | --- |
| Team Members | Malak Hassan Mahmoud Eman Ali Mostafa Farah Khaled Fathy Mariam Baher Mohsen Menna AbdelNasser Ramadan |
| Instructor | Nouran Elzeky |
| Version / Date | v1.0 · 31 October 2026 |

# Project: DevCompare – Development Indicators Comparison Across Five Countries

Objective: Build a data-analysis project that compares the development of Egypt, Nigeria, India, Brazil and Türkiye (2000–2025) using World Bank World Development Indicators (WDI), and presents the results in an interactive dashboard with rankings, a transparent Development Score and a simple trend forecast to 2030.

Description: The team received two WDI Excel extracts (21 countries with ~70 indicators, and Egypt + Nigeria). The project merges and cleans them, keeps five countries and 18 well-covered indicators in six themes (Economy, Structure & Trade, Population & Labor, Health, Infrastructure) plus one derived indicator (GDP per capita), runs the analysis, and publishes the results as Excel/CSV files, static charts and a single-file HTML dashboard. Known data issues (year 2009 missing for all countries; Egypt missing 2009–2015) are handled openly: gaps are interpolated and flagged.

Tools & Design: Draw.io-style UML diagrams (generated with Graphviz), wireframes for desktop and mobile, GitHub for version control, Excel for results and review.

Technologies to Use: Python 3, pandas, NumPy, scikit-learn (linear trend), matplotlib, openpyxl, HTML/CSS/JavaScript with Chart.js, unittest, Git/GitHub.

Team Members & Responsibilities:

- Shahd Mahmoud Abdelmagid – Team Leader · Project Manager: Leads the team and speaks on its behalf; owns the GitHub repository (company organisation account) and uploads all files; plans weeks and milestones; integrates modules; leads the final presentation.

- Malak Hassan Mahmoud – Data Engineer: Data ingestion and cleaning (data_loader.py): merging the two WDI extracts, missing-value handling, interpolation rules, data quality report.

- Eman Ali Mostafa – Data Analyst: Analytics (analysis.py): ranking, CAGR, correlation, Development Score and forecasting; writes the insights and interpretation.

- Farah Khaled Fathy – Dashboard & Visualization Developer: Interactive dashboard (template.html, export_dashboard.py) and static charts (charts.py).

- Mariam Baher Mohsen – Systems Analyst & Designer: Requirements gathering, use cases, UML diagrams, ER diagram and schema, UI/UX wireframes and guidelines.

- Menna AbdelNasser Ramadan – QA Engineer & Documentation Lead: Test plan, test cases, automated tests, bug reports, user manual, technical documentation and presentation material.

Note: the role assignment below is a proposal prepared with the project documents. The team must confirm or adjust it and tell the instructor within the deadline, because the final evaluation depends on each member explaining what they actually did.

# Week 5: Team formation & planning – Shahd (lead), all members

- Form the 6-member team, appoint Shahd as Team Leader

- Choose the project idea and the five countries

- Explore the two WDI extracts (countries, indicators, years)

- Draft this proposal using the DEPI template

Deliverables:

- Team list and leader confirmed

- Draft Project Proposal

# Week 6: Proposal finalisation – Shahd, Mariam, Menna

- Define objectives, scope and success KPIs

- Write the risk list (data gaps, scope, availability)

- Prepare the Gantt chart and milestones

- Create the GitHub repository structure

Deliverables:

- Final Project Proposal

- Project Plan (Gantt)

# Week 7: Instructor review – Shahd, Nouran Elzeky (instructor)

- Submit the proposal to the instructor for approval

- Collect feedback and suggested improvements

- Freeze the final team list (end of week 7)

Deliverables:

- Instructor feedback log

- Approved proposal

# Week 8: Task division & scope freeze – Shahd, all members

- Divide responsibilities per member

- Agree on the branching strategy and commit rules

- Agree on the indicator list (18 indicators + 1 derived)

Deliverables:

- Task Assignment & Roles table

- Scope statement

# Week 9: Requirements gathering I – Mariam, Eman

- Stakeholder analysis

- Write user stories

- Final task list presented again to the instructor (end of week 9)

Deliverables:

- Stakeholder analysis

- User stories

# Week 10: Requirements gathering II – Mariam, Eman, Menna

- Write use cases and descriptions

- Write functional requirements

- Write non-functional requirements

Deliverables:

- Use cases

- FR and NFR lists

# Week 11: Requirements sign-off & data profiling – Malak, Mariam

- Review requirements with the instructor

- Profile data quality: missing years, empty indicators

- Decide the gap-handling rule (interpolate ≤ 7 years, flag)

Deliverables:

- Requirements Specification v1.0

- Data profiling notes

# Week 12: Analysis & design I – Mariam, Malak

- Problem statement and objectives

- Use case diagram

- Software architecture (pipeline + static dashboard)

Deliverables:

- Use case diagram

- Architecture diagram

# Week 13: Analysis & design II – Mariam, Malak, Eman

- ER diagram and logical/physical schema

- DFD level 0 and level 1

- Define analytics formulas (CAGR, score, forecast)

Deliverables:

- ERD + schema

- DFDs

# Week 14: Analysis & design III – Mariam, Farah

- Sequence, activity, state and class diagrams

- Wireframes and mock-ups

- UI/UX guidelines

Deliverables:

- UML set

- Wireframes

# Week 15: Design review – Shahd, all members

- Deployment and component diagrams

- Technology stack decision

- Design review with the instructor

Deliverables:

- System Analysis & Design document

- Approved design

# Week 16: Implementation I – Malak, Shahd

- Project skeleton, configuration module

- Data loader: read, merge, clean

- Interpolation and derived GDP per capita

Deliverables:

- config.py, data_loader.py

- Processed CSV + quality report

# Week 17: Implementation II – Eman, Malak

- Ranking and CAGR

- Development Score and correlation

- Forecast with hold-out MAE

Deliverables:

- analysis.py

- Results workbook (xlsx)

# Week 18: Implementation III – Farah, Eman

- Static charts

- Interactive dashboard (filters, KPI cards, tables)

- Dark/light mode and responsive layout

Deliverables:

- charts.py, dashboard.html

- README

# Week 19: Testing & QA – Menna, all members

- Run unit tests and fix defects

- Run user-acceptance cases in the browser

- Write bug reports

Deliverables:

- Test report

- Bug reports

# Week 20: Documentation & presentation – Menna, Mariam, Shahd

- User manual and technical documentation

- Infographic and presentation

- Final upload of all files to GitHub

- Rehearse the presentation – each member explains own work

Deliverables:

- User manual

- Technical documentation

- Infographic + PPT/PDF

# Week 21: Release & final presentation – all members

- Final discussion (usually the same time as the lecture)

- Every member presents and explains own responsibility

- Attendance is mandatory

Deliverables:

- Final presentation

- Release of the repository